## ISO27005 Risk Register
Risk ID | Threat Scenario | Asset(s) Affected | Threat Source | Vulnerability Exploited | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Rating | Treatment Option | Treatment Control(s) - Annex A Ref | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Rating | Risk Owner | Status
RR-01 | Compromised engineer credentials via phishing used to access production payroll database | Production RDS (payroll DB), Okta identities | External attacker | Lack of phishing-resistant MFA on all privileged paths | 4 | 5 | 20 | Critical | Mitigate | A.5.17, A.8.2, A.8.5 (phishing-resistant MFA, JIT privileged access) | 2 | 5 | 10 | High | Head of IT/Security | Treated
RR-02 | Misconfigured S3 bucket exposes employee PII to the public internet | S3 buckets (employee records, payslips) | External attacker / opportunistic scanning | Absence of automated public-access-block enforcement on new buckets | 3 | 5 | 15 | High | Mitigate | A.8.9, A.5.23, A.8.12 (config management, cloud security baseline, DLP) | 1 | 5 | 5 | Medium | VP Engineering | Treated
RR-03 | Privileged insider (DevOps engineer) exfiltrates banking/direct-deposit data | Production RDS (payroll DB) | Malicious insider | Excessive standing privileged access without segregation of duties | 3 | 5 | 15 | High | Mitigate | A.5.3, A.8.2, A.8.15, A.8.16 (segregation of duties, privileged access, logging, monitoring) | 2 | 5 | 10 | High | CISO | Treated
RR-04 | Ransomware encrypts production RDS and backup snapshots simultaneously | Production RDS, backup snapshots | External attacker (ransomware) | Backups reachable from same IAM trust boundary as production | 4 | 5 | 20 | Critical | Mitigate | A.8.13, A.5.15 (backup isolation, access control segregation) | 2 | 4 | 8 | Medium | VP Engineering | Treated
RR-05 | Third-party ACH/SEPA banking rail partner suffers a breach exposing PayBridges customer banking data in transit | Payment integration interfaces | Third-party/supplier failure | Insufficient supplier due diligence and monitoring of sub-processor security posture | 3 | 5 | 15 | High | Mitigate | A.5.19, A.5.20, A.5.22 (supplier relationships, contractual security terms, supplier monitoring) | 2 | 5 | 10 | High | Head of Legal & Compliance | Treated
RR-06 | Insecure Direct Object Reference (IDOR) in payroll API exposes one tenant's data to another tenant | Payroll microservice API | External attacker / malicious customer user | Missing tenant-scoped authorization checks at the API layer | 3 | 5 | 15 | High | Mitigate | A.8.26, A.8.28, A.8.29 (application security requirements, secure coding, security testing) | 1 | 5 | 5 | Medium | VP Engineering | In Progress
RR-07 | Unpatched critical CVE in container base image is exploited to gain container escape | ECS containers (all microservices) | External attacker | Delayed patch/vulnerability management cadence for base images | 3 | 4 | 12 | High | Mitigate | A.8.8, A.8.9 (vulnerability management, configuration management) | 2 | 4 | 8 | Medium | VP Engineering | Treated
RR-08 | GitHub Actions secrets are leaked via a compromised third-party Action, enabling malicious code injection into the deployment pipeline | CI/CD pipeline, production deploy credentials | External attacker (supply chain) | Use of unpinned/unverified third-party GitHub Actions with broad secret scope | 3 | 5 | 15 | High | Mitigate | A.8.32, A.5.21, A.8.9 (change management, ICT supply chain, config management) | 2 | 4 | 8 | Medium | VP Engineering | In Progress
RR-09 | Terminated employee's access is not revoked in time, enabling continued system access post-termination | Okta, AWS IAM, GitHub org access | Disgruntled former employee | Manual, non-automated offboarding process dependent on HR ticket timeliness | 3 | 4 | 12 | High | Mitigate | A.6.5, A.5.16, A.5.18 (post-termination responsibilities, identity management, access review) | 1 | 4 | 4 | Low | Head of People | Treated
RR-10 | Distributed Denial of Service (DDoS) attack against the customer payroll portal during a scheduled pay-run window | Customer-facing web application, ALB/CloudFront | External attacker (hacktivist/extortion) | No managed DDoS mitigation service in front of customer-facing endpoints | 2 | 4 | 8 | Medium | Mitigate | A.8.6, A.8.14 (capacity management, redundancy of processing facilities) | 1 | 3 | 3 | Low | VP Engineering | Treated
RR-11 | Loss or mismanagement of AWS KMS Customer Master Key renders encrypted payroll data permanently unrecoverable | AWS KMS, all encrypted Restricted data | Operational error / negligent insider | No documented key rotation/backup and recovery procedure for CMKs | 2 | 5 | 10 | High | Mitigate | A.8.24, A.5.37 (use of cryptography, documented operating procedures) | 1 | 5 | 5 | Medium | VP Engineering | Treated
RR-12 | Insufficient logging and monitoring delays detection of an active breach beyond the containment window | All production systems | N/A (detective control gap) | Inconsistent log retention and absence of centralized alerting on anomalous access patterns | 3 | 4 | 12 | High | Mitigate | A.8.15, A.8.16, A.5.25 (logging, monitoring, assessment of security events) | 2 | 3 | 6 | Medium | CISO | In Progress
RR-13 | Cross-border transfer of EU employee PII to US-region infrastructure without an adequate transfer mechanism | EU customer employee PII | Regulatory / compliance risk | No documented Standard Contractual Clauses or region-pinning for EU tenant data | 2 | 4 | 8 | Medium | Mitigate | A.5.31, A.5.34 (legal/regulatory requirements, privacy and protection of PII) | 1 | 3 | 3 | Low | Head of Legal & Compliance | Treated
RR-14 | Compromised open-source dependency (npm/pip package) introduces malicious code into the payroll application | Application build pipeline, production containers | External attacker (supply chain) | No software composition analysis (SCA) or dependency pinning enforced in CI | 3 | 4 | 12 | High | Mitigate | A.8.28, A.8.8, A.5.21 (secure coding, vulnerability management, ICT supply chain) | 2 | 3 | 6 | Medium | VP Engineering | In Progress
RR-15 | Business email compromise targeting Finance to redirect a customer's payroll disbursement to a fraudulent account | Finance/Payments team, banking rail integration | External attacker (social engineering / BEC) | No out-of-band verification requirement for changes to customer bank account details | 3 | 5 | 15 | High | Mitigate | A.6.3, A.5.24 (security awareness training, incident management planning) | 2 | 4 | 8 | Medium | Head of Legal & Compliance | Treated
RR-16 | Untested disaster recovery plan fails during an actual regional AWS outage, extending a pay-run outage beyond SLA | Production infrastructure (multi-AZ/region) | Environmental / cloud provider outage | DR runbook exists but has not been tested via a live failover exercise | 3 | 4 | 12 | High | Mitigate | A.5.29, A.5.30 (information security during disruption, ICT readiness for business continuity) | 2 | 3 | 6 | Medium | VP Engineering | In Progress
RR-17 | Privileged DevOps engineer directly modifies payroll records in production outside the change management process | Production RDS (payroll DB) | Malicious or negligent insider | Standing direct database write access without an approved-change gate | 2 | 5 | 10 | High | Mitigate | A.8.32, A.5.3, A.8.16 (change management, segregation of duties, monitoring) | 1 | 4 | 4 | Low | VP Engineering | Treated
RR-18 | Lost or stolen employee laptop containing locally cached customer PII is accessed by an unauthorized party | Employee endpoints | Opportunistic theft | Inconsistent enforcement of full-disk encryption and remote wipe across all endpoints | 2 | 4 | 8 | Medium | Mitigate | A.7.9, A.8.1, A.5.11 (assets off-premises, endpoint devices, return of assets) | 1 | 3 | 3 | Low | Head of IT/Security | Treated
RR-19 | Sub-processor providing transactional email delivery (payslip PDFs) suffers a breach exposing message content | Email delivery sub-processor integration | Third-party/supplier failure | Payslip PDFs transmitted as attachments rather than via secure portal link | 3 | 4 | 12 | High | Mitigate | A.5.19, A.5.20, A.8.24 (supplier relationships, supplier agreements, cryptography) | 2 | 3 | 6 | Medium | Head of Legal & Compliance | In Progress
RR-20 | SQL injection in a legacy reporting module allows unauthorized data extraction | Legacy reporting microservice | External attacker | Legacy module not yet migrated to the parameterized-query standard used elsewhere | 2 | 5 | 10 | High | Mitigate | A.8.28, A.8.29, A.8.26 (secure coding, security testing, application security requirements) | 1 | 4 | 4 | Low | VP Engineering | In Progress

## Legend & Methodology Ref
Legend
Likelihood / Impact scale | 1=lowest, 5=highest — see Risk_Assessment_Methodology.md Section 3-4
Inherent Risk Score | Likelihood x Impact (before treatment)
Residual Risk Score | Residual Likelihood x Residual Impact (after treatment/control in place)
Rating bands | Low 1-4 ¦ Medium 5-8 ¦ High 9-15 ¦ Critical 16-25
Treatment Options | Mitigate / Transfer / Avoid / Accept
Status values | Treated = control implemented & operating ¦ In Progress = control being implemented ¦ Accepted = formally risk-accepted
Source | Methodology per ISO/IEC 27005:2022 — see 02_Risk_Management/Risk_Assessment_Methodology.md